## Library Science
Goal 1: Fullerton College will promote student success.
Objective 1: Address the needs of under-prepared students.
Action | Resources | Responsibility | Timeframe | Outcomes
The Library will assess its technology program based on the identified SLO. | Library staff for the distribution of the survey to library technology users. | Circulation and Systems librarians. | Fall 2014: | Add results to library technology plan to provide support for future library technology budgeting and purchasing.
Write a survey assessing library technology program.
Librarian time to create & distribute assessments, collect & analyze data, and implement changes.
Survey library technology users (every fourth semester).
Assess results.
Spring 2015:
Revise library technology program if results warrant and funds allow.
Implement changes to library policies, as necessary.
Action 1.1.22
The Library will assess its website usability based on the identified SLO. | Librarian time to create & distribute assessments, collect & analyze data, and revise website if results warrant and funds allow. | Systems Librarian. | Fall 2014: | Improve and/or strengthen the usability of the library website.
Write a survey assessing library website usability.
Survey library website users (every fourth semester).
Assess results.
Spring 2015:
Revise library website if results warrant and funds allow.
Action 1.1.23
The Library will develop library orientations for new students based on level of interest shown on Spring 2013 questionnaires. | Librarian time to create & distribute advertisements for the orientations. | Circulation Librarian. | Develop freshman library orientations for Fall 2013. | Develop new student orientations to give entering students’ knowledge about library services that will help them succeed academically. Pass-out short follow-up questionnaire to evaluate effectiveness of new orientations.
Action 1.1.24
The Library will assess its collections of basic skills print books based on an identified SLO. | Librarians’ time to create surveys in print and online versions as well as to administer these to students. | Acquisitions and Catalog librarians will create and administer these surveys. | Fall 2013: Create print and online surveys. | Improve content of the basic skills collections to better assist students with their school work.
|  | All librarians will evaluate the results of the surveys. | Spring 2014:
Administer surveys to students.
Fall 2014:
Evaluate results of surveys.
Spring 2015:
Update collections if survey results warrant and funds allow.
Action 1.1.25
The Library will develop resource guides in selected subject areas. | Librarian time to create, distribute, market, assess, collect & analyze data, and implement changes. | Select librarians. | Fall 2013: Librarians will create at least one resource guide in their collection area and promote to department faculty. | Create greater awareness of library resources.
Librarians will send out feedback survey to faculty at the end of semester and track the number of page views. Librarians will analyze & discuss how to improve or strengthen guides and/or awareness of guides.
Spring 2014: Librarians will create at least one resource guide in their collection area and promote to department faculty.
Repeat assessment, analysis, and implementation of changes.
Fall 2014: Librarians will create at least one resources guide in their collection areas and promote to dept.
Repeat assessment, analysis, and implementation of changes.
Spring 2015: Librarians will create at least one resource guides in their collection area and promote to department faculty.
Repeat assessment, analysis, and implementation of changes.
Action 1.1.26
Library Technology will offer a section of LIB 100F – Introduction to Research for Buena Park High School (BPHS) Students. | Course and transportation will be funded by the Fullerton Joint Union High School District (FJUHSD). | Dean of Library Technology and VPI | Spring 2014 | A section of LIB 100 for BPHS students will be offered Summer 2013. Students will be provided transportation to the college by the Fullerton Joint Union High School District (FJUHSD).
Goal 1: Fullerton College will promote student success.
Objective 2: Increase course retention and success.
Action | Resources | Responsibility | Timeframe | Outcomes
Increase the number of students receiving information literacy instruction at the library. | Librarian time to create various modes of instruction that will provide access to a greater number of students. | Instruction librarian will develop & improve online guides & labs and assessments with input from other librarians. | Fall 2013: Revise Selecting Sources online lab & assessments. Create assessment for MLA online lab. | Increased number of students attending library instruction sessions, requesting research consultations, seeking research assistance at the reference desk (in-person and online), viewing library research guides, and participating in library online labs.
| Librarian time to promote these various modes of instruction. | Instruction librarian will collect assessment data. | Towards the end of the semester, advertise these labs to instructors, suggesting they use labs as extra credit or assignment.
|  | All librarians will analyze data to make recommendations for revising guides, labs, and/or assessments. | Spring 2014: In the beginning of semester, promote labs with instructors. At the end of the semester, analyze assessment data to improve online lab instruction for Fall 2014.
Goal 3: Fullerton College will strengthen connections with the community.
Objective 2: Strengthen partnerships with local feeder high schools and universities.
Action | Resources | Responsibility | Timeframe | Outcomes
Action 3.2.10
The Library will develop, communication and collaboration with high schools to help improve college readiness of high school graduates. | Campus announcements and flyers sent via email. | Dean of LLRC | Principals’ breakfast, Fall 2013 through Spring 2015 | Improve research skills of high school graduates.
Goal 1: Fullerton College will promote student success.
Objective 2: Increase course retention and success.
Action | Resources | Responsibility | Timeframe | Outcomes
Action 1.2.15
Increase the number of students receiving information literacy instruction at the library. | Librarian time to create various modes of instruction that will provide access to a greater number of students. | Instruction librarian will develop & improve online guides & labs and assessments with input from other librarians. | Fall 2013: Revise Selecting Sources online lab & assessments. Create assessment for MLA online lab. | Increased number of students attending library instruction sessions, requesting research consultations, seeking research assistance at the reference desk (in-person and online), viewing library research guides, and participating in library online labs.
| Librarian time to promote these various modes of instruction. | Instruction librarian will collect assessment data. | Towards the end of the semester, advertise these labs to instructors, suggesting they use labs as extra credit or assignment.
|  | All librarians will analyze data to make recommendations for revising guides, labs, and/or assessments. | Spring 2014: In the beginning of semester, promote labs with instructors. At the end of the semester, analyze assessment data to improve online lab instruction for Fall 2014.
Action 1.2.16
The Library will assess its collections (subscription databases and print books), based on an identified SLO. | Librarians’ time to create surveys in print and online versions as well as to administer these to students. | Acquisitions and Catalog librarians will create and administer these surveys. | Fall 2013: Create print and online surveys. | Improve content of the collections to better assist students with their school work.
|  | All librarians will evaluate the results of the surveys. | Spring 2014:
Administer surveys to students.
Fall 2014:
Evaluate results of surveys.
Spring 2015:
Update collections if survey results warrant and funds allow.
The Library will continue to scan and review available grant opportunities to strengthen library resources. | Library faculty and dean | Acquisitions librarian and library staff | Librarians will collaborate to determine funding priorities. | Improve library resources and
Acquisitions librarian will submit grants on an ongoing basis, as time allows.
Goal 2: Fullerton College will reduce the achievement gap.
Objective 1: Address the needs of English language learners.
Action | Resources | Responsibility | Timeframe | Outcomes
Action 2.1.4
The Library will assess its collection of ESL print books based on an identified SLO. | Librarians’ time to create surveys in print and online versions as well as to administer these to students. | Acquisitions and Catalog librarians will create and administer these surveys. | Fall 2013: Create print and online surveys. | Improve content of the ESL collections to better assist students with their school work.
|  | All librarians will evaluate the results of the surveys. | Spring 2014:
Administer surveys to students.
Fall 2014:
Evaluate results of surveys.
Spring 2015:
Update collections if survey results warrant and funds allow.

## All Divisions
Goal 1: Fullerton College will promote student success. Objective 1: Address the needs of under-prepared students.
BUSINESS & CIS
Action 1.1.3
The Business & CIS Division will utilize early diagnostic tools in Business Writing and Business Communications classes to identify under-prepared students in writing skills and refer them to the Academic Support Center. | Business Administration and Management faculty teaching BUS 111 and BUS 211. | Business Administration and Management faculty teaching BUS 111 and BUS 211. | Planning Fall 2013 with implementation in Spring 2014. | Diagnostic implemented uniformly across all sections taught by FT and adjunct faculty, with referrals for at-risk students.
COUNSELING
Action 1.1.4
The Counseling Division will increase the number of service area, first time students who apply, complete orientation and assessment during the first month of open application. | SARS Call software & communication hardware, campus website, CCC Apply application, staff for high school presentations. | Stewart Kimura, Greg Menchaca, Rolando Sanabria | Fall 2013-Spring 2015 | More service area, first time students will complete application, the orientation (and receive minimum score on exit quiz) and assessment during the first month of open registration.
Action 1.1.5
The Counseling Division will enhance security and functionality of online math pre-test tool / website. | ACT technical staff, campus web servers. | Matriculation Coordinator | Fall 2013-Spring 2015 | Security of math pre-test website will be increased to mitigate vulnerability to “hacking”, functionality of website will be repaired.
Action 1.1.6
The Counseling Division - Career & Life Planning Center will enhance presentations for Freshmen Orientation. | CACareerCafe, CLPC Website, FC Catalog, SB1456 | CLP Center Coordinator | Each Fall Aug 2013-2015 | Students will develop awareness of Career Planning Process
Action 1.1.7
The Counseling Division will educate high school special education staff, parents and students about necessary readiness criteria to be successful at a credit institution so these can be incorporated into the students’ transition planning.(Post SB 1456 implementation) | Additional DSS counseling hours to create content | DSS Director and DSS Counselor. | Fall 2013 and on-going | Students with appropriate college readiness skills will be more successful – resulting in high success and completion rates in DSS students overall.
Action 1.1.8
The Counseling Division will design and implement new and creative methods to address basic skills deficiencies in DSS students. | Additional DSS instructional staffing to develop and implement. | DSS Director, DSS instructor | Fall 2013 and on-going | Improve DSS student success and completion rates in Basic Skills courses.
FINE ARTS
Action 1.1.9
Fine Arts will recruit representative faculty to serve on the Student Success and Basic Skills Committees and engage in developing new strategies for increasing awareness for the needs of under-prepared students in Fine Arts. | Time | Bob Jensen | Summer, fall 2013 | Improved student degree and certificate rates among underprepared students
|  | Jim Dowdalls (Art) | spring 2014
|  | Tony Mazzaferro (Music) |  | Improved faculty advisement strategies and teaching strategies
Steve Pliska (Theatre)
Action 1.1.10
The Fine Arts Division will use centennial events to celebrate student success stories to encourage under-prepared students to become successful college students | Centennial budget | Bob Jensen | Summer, Fall 2013 | Improved student motivation
|  | Andrea Hanstein | Spring 2014
|  | Stephanie Reyna |  | Increased awareness of successful role models for student success in specific college programs
HUMANITIES
Action 1.1.11
The English Department will conduct faculty led workshops focusing on best practices. | None requested | English Department Coordinator | Planning and implementation during Fall 2013 and Spring 2014. | Positive survey results of department members, who participate in the Best Practices Discussion Group and a summary report during a department meeting.
Action 1.1.12
The English Department will increase the number of faculty trainings to teach the pilot accelerated composition course. | None requested | English Department Coordinator | English Department faculty will train through the “Community of Practice in Acceleration” statewide group June 29-July 1, 2013. More faculty teaching sections of accelerated English in Spring 2014. | An increase in the number of students participating in the acceleration pilot.
Action 1.1.13
The ESL Department will engage in a dialog with the Counseling Department on placement considerations. | None requested | ESL Department Coordinator and Faculty | Fall 2013 – Spring 2015 | There will be an increase in the number of students taking the ESL placement test, which in turn will result in students being correctly placed in ESL classes rather than English.
Action 1.1.14
The Humanities Division - ESL Department will implement and evaluate the success of two Directed Learning Activities for ESL 186. | Assistance from the Institutional Research Office. | ESL Department Coordinator and Faculty | Fall 2013 – Spring 2015 | Increased success rate of ESL 186 students completing DLAs.
Higher performance on classroom measures of skills covered in DLAs.
Action 1.1.15
The Humanities Division - Reading Department will continue to develop and research accelerated curriculum in reading and pilot the concept in Spring 2014. | Basic Skills Initiative support for attendance at relevant workshops or conferences. | Reading Department Coordinator and Faculty | Fall 2013- Spring 2014 | Curriculum development, planning, and piloting of a department accelerated course.
Action 1.1.16
The Speech Department will conduct workshops on teaching strategies in department meetings. | None requested | Speech Department Coordinator and Faculty | Fall 2013 | Updates to Curriculum in Six-Year Review.
Action 1.1.17
The Transfer Achievement Program will require TAP students whose placement is below Read 142 to take a reading class. | Extended day budget for course sections. | TAP Planning Committee | 2013-2014: Add additional section of Read 56 and seats in Read 36, 56, and 96 | Increased student success and retention.
|  | Carol Shier, Coordinator |  | Additional seats in reading courses available for TAP students.
Action 1.1.18
The Transfer Achievement Program will identify strengths and weaknesses of the program in order to drive improvement. | Cohort tool or other tools in Banner and time provided by Institutional Researcher. | TAP Planning Committee | Fall 2013 Request provided to Institutional Researcher | Based on what works, develop strategies for improvement.
|  | Carol Shier, Coordinator | Spring 2014 Review of data
Institutional Researcher
Action 1.1.19
The Student Success Committee will undertake an initiative that will focus on incorporating habits of mind for success into instruction and student services. | College general funds for supplies ($1000), honoraria for speakers ($500), and web design services ($1500). | Student Success Committee Co-chairs | Fall 2013-Explore | Students will be better prepared for courses across the curriculum.
Spring 2014-Pilot
Fall 2014-Implement
Spring 2015-Evaluate
Action 1.1.20
The Student Success Committee will work with the Staff Development Committee and the Basic Skills Committee to create a sustained professional development program for new faculty. | Adequate support for the Staff Development Office. | Student Success Committee Co-chairs with assistance from the Basic Skills Co-chairs and Staff Development Coordinator | Fall 2013-Spring 2014-Planning | Faculty will be better prepared to teach FC students.
Fall 2014-Implement
LIBRARY & LEARNING RESOURCES
Action 1.1.21
The Library will assess its technology program based on the identified SLO. | Library staff for the distribution of the survey to library technology users. | Circulation and Systems librarians. | Fall 2014: | Add results to library technology plan to provide support for future library technology budgeting and purchasing.
Write a survey assessing library technology program.
Librarian time to create & distribute assessments, collect & analyze data, and implement changes.
Survey library technology users (every fourth semester).
Assess results.
Spring 2015:
Revise library technology program if results warrant and funds allow.
Implement changes to library policies, as necessary.
Action 1.1.22
The Library will assess its website usability based on the identified SLO. | Librarian time to create & distribute assessments, collect & analyze data, and revise website if results warrant and funds allow. | Systems Librarian. | Fall 2014: | Improve and/or strengthen the usability of the library website.
Write a survey assessing library website usability.
Survey library website users (every fourth semester).
Assess results.
Spring 2015:
Revise library website if results warrant and funds allow.
Action 1.1.23
The Library will develop library orientations for new students based on level of interest shown on Spring 2013 questionnaires. | Librarian time to create & distribute advertisements for the orientations. | Circulation Librarian. | Develop freshman library orientations for Fall 2013. | Develop new student orientations to give entering students’ knowledge about library services that will help them succeed academically. Pass-out short follow-up questionnaire to evaluate effectiveness of new orientations.
Action 1.1.24
The Library will assess its collections of basic skills print books based on an identified SLO. | Librarians’ time to create surveys in print and online versions as well as to administer these to students. | Acquisitions and Catalog librarians will create and administer these surveys. | Fall 2013: Create print and online surveys. | Improve content of the basic skills collections to better assist students with their school work.
|  | All librarians will evaluate the results of the surveys. | Spring 2014:
Administer surveys to students.
Fall 2014:
Evaluate results of surveys.
Spring 2015:
Update collections if survey results warrant and funds allow.
Action 1.1.25
The Library will develop resource guides in selected subject areas. | Librarian time to create, distribute, market, assess, collect & analyze data, and implement changes. | Select librarians. | Fall 2013: Librarians will create at least one resource guide in their collection area and promote to department faculty. | Create greater awareness of library resources.
Librarians will send out feedback survey to faculty at the end of semester and track the number of page views. Librarians will analyze & discuss how to improve or strengthen guides and/or awareness of guides.
Spring 2014: Librarians will create at least one resource guide in their collection area and promote to department faculty.
Repeat assessment, analysis, and implementation of changes.
Fall 2014: Librarians will create at least one resources guide in their collection areas and promote to dept.
Repeat assessment, analysis, and implementation of changes.
Spring 2015: Librarians will create at least one resource guides in their collection area and promote to department faculty.
Repeat assessment, analysis, and implementation of changes.
Action 1.1.26
Library Technology will offer a section of LIB 100F – Introduction to Research for Buena Park High School (BPHS) Students. | Course and transportation will be funded by the Fullerton Joint Union High School District (FJUHSD). | Dean of Library Technology and VPI | Spring 2014 | A section of LIB 100 for BPHS students will be offered Summer 2013. Students will be provided transportation to the college by the Fullerton Joint Union High School District (FJUHSD).
MATHEMATICS & COMPUTER SCIENCE
Action 1.1.28
The Mathematics and Computer Science Division will develop a series of boot campus or other interventions prior to the beginning of class to better prepare students for mathematics classes | Reassigned time and/or faculty stipends to develop the boot camps either on campus or online | Mathematics Faculty | Begin discussion in Fall 2013, with possible pilot in winter intersession January 2014 | Better prepared students in mathematics classes
Materials to be used in the interventions, such as skill-building software
Action 1.1.29
The Mathematics and Computer Science Division will continue to refine placement processes, including alternatives to the COMPASS test, better use of multiple measures, and the use of faculty advisors | Reassigned time and/or faculty stipends to work with Matriculation and Counseling | Mathematics and Computer Science Division Dean and Mathematics Faculty | Ongoing. In conjunction with the results of the current Professional Learning Council, and the task force developed by the Student Success Committee | Better placement. Shorter pathways for students to move through the basic skills sequence
| Funds to potential purchase diagnostic software (such as My Math Test) and a dedicated Computer Lab in which to offer remediation and tutoring | Matriculation and Counseling
Action 1.1.30
The Mathematics and Computer Science Division will restructure curriculum into an intensive review of arithmetic (MATH 007 F), a redesigned MATH 015 F (Pre-Algebra) and MATH 020 F (Beginning Algebra) | None requested | Mathematics Faculty | MATH 007 F will be offered for the first time in Fall 2014. At that time MATH 015F will have all prerequisites removed, and MATH 020 F will have MATH 015 F as an advisory only | Only students who clearly show the need for intensive arithmetic instruction will be placed into MATH 007 F. MATH 015 F or MATH 020 F will serve as the “entry-level” course to the basic skills mathematics sequence
NATURAL SCIENCES DIVISION
Action 1.1.31
The Natural Sciences Division will maintain & expand GPS2 (Guiding and Preparing Science, Technology, Engineering, and Math Students) efforts | STEM/GPS2 Coordinator | Natural Sciences Division Dean and Faculty, Office of Special Programs | Ongoing, with expansion in 2013 – 2015 | Students entering STEM courses will be better prepared and receive appropriate support
Dedicated space for tutoring and support
Supplies/Materials
Action 1.1.32
The Natural Sciences Division will continue the Maximizing Student Potential (MSP) program | Funds for the program | Natural Sciences | Ongoing with expansion in 2013 – 2015 | Increased advising and tutoring of STEM majors
Division Dean and Faculty, Office of Special Programs
Action 1.1.33
The Natural Sciences Division will request a counselor trained to specialize in STEM majors and will participate in the development of STEM majors guides | None requested | Natural Sciences | Fall 2013 | Underprepared students will have a dedicated counselor with whom to discuss placement and other issues
Division Dean, Counseling Dept.
Action 1.1.34
The Natural Sciences Division will research and examine methods to better prepare students for its curriculum | None requested | Natural Sciences Division Dean and Faculty | Incorporated into departmental 6-yr curriculum review cycle | Possible inclusion of prerequisites on various entry-level science courses
Action 1.1.35
The Natural Sciences Division will implement a science related orientation program | Budget for boot-camp activities including faculty stipends and materials | Natural Sciences Division Dean and Faculty, Office of Special Programs | Summer 2014 | Students better prepared for entry-level science courses
PHYSICAL EDUCATION
Action 1.1.36
The Physical Education Division will expand the Incite Program for all student-athletes | Title III | Director of Academic Support Center; Tutoring Center Coordinator | Expand 2013-15 | Improved academic success for student-athletes.
Action 1.1.37
The Physical Education Division will strengthen testing in core classes for student athlete transfer. | Title III | Incite Director | 2013-15 | Improved academic success for student-athletes
PUBLIC INFORMATION
Action 1.1.38
The Public Information Office will publish a monthly, internal student newsletter highlighting the programs and services offered by the college. | Department budget | Public Information Officer | 2013-15 | Increased awareness of resources available to under-prepared students.
Marketing & Outreach Assistant
Action 1.1.39
The Public Information Office will establish a formal Student Ambassador Program. | Department budget | Public Information Officer | 2013-15 | Increased awareness of resources available to under-prepared students.
|  | Marketing & Outreach Assistant |  | Increased opportunities for peer-to-peer interaction.
SOCIAL SCIENCES
Action 1.1.40
Ensure Social Sciences Divisional participation in the Student Success Committee and the initiatives sponsored by it. | None requested | Social Sciences Division Dean | 2013 -- 2015 | Improved course success of under-prepared students.
Action 1.1.41
The Social Sciences Division will expand the use of tutors and interns in selected sections of course offerings. | Basic Skills | Social Sciences Division Dean | 2013 -- 2015 | Improved course success of under-prepared students.
Student Success
Action 1.1.42
Social Sciences faculty will develop best practices and present as workshops, pedagogy designed to improve learning in large lecture settings. | None requested | Social Sciences Division Dean | 2013 -- 2015 | Improved course success of under-prepared students.
STUDENT SERVICES DIVISION
Action 1.1.43
The Student Services Division will develop a pilot program of “Jump Start to College” bringing approximately 500 8th grade students to the campus | Vital Link | Vice President, Student Services | Implement Spring 2014 | 8th graders will learn importance of high school courses and grades for preparation for college; information about the community college system; and about services and programs available at Fullerton College.
| Outreach funds | Dean of Counseling
Dean of Student Support Services
STUDENT SUPPORT SERVICES
Action 1.1.44
The EOPS Program will increase outreach services to include 13 feeder high schools for recruiting of students to the annual “College Prep Conference”. | EOPS Staff and Faculty. | EOPS Outreach Coordinator, EOPS Faculty and Staff. | 2013 - 2015 | Students will acquire the necessary knowledge to understand the college admissions and matriculations processes. These practices include the admissions process, and financial aid awareness.
Provide Surveys to attending students.
Process data generated by surveys.
Action 1.1.45
The Financial Aid Office will implement more efficient methods of communicating with and serving students applying for financial aid. | Financial Aid Office | Director of Financial Aid | Currently implementing for fall 2013. | Communication with students will be more immediate by moving from email based notification to targeted announcements in myGateway. Students will receive immediate notification on their financial aid file by logging in to their student portal. This will reduce student concerns from not receiving notification in a timely manner due to spam filters, etc.
Action 1.1.46
Student Affairs will encourage A.S., ICC, Clubs and Organizations to form student groups and provide in-meeting presentations to promote student success | Inter-Club Council/ICC | Student Affairs Staff will collaborate with A.S., ICC and the Clubs & Organizations in providing educational presentations during meetings and to support study sessions on campus | Fall 2013-Spring 2014 | To increase the number of A.S. ICC and clubs study groups, and in-meeting educational presentations to enhance student success and address the needs of under-prepared students.
Clubs and Organizations
Associated Students
Student Affairs Staff
FC Master Calendar
Action 1.1.47
Student Affairs will direct and support Inter-Club Council and the Club Collaborative in providing ICC Food Drive efforts for the FC Food Bank. | Student Affairs Staff | Director, Student Activities/ICC Advisor to provide direction and advisement | The ICC Food Drive proposal was approved by ICC in April 2013. | To promote and provide weekly to monthly canned goods and dry goods, as donated, for the FC Food Bank.
| Inter-Club Council/ICC |  | ICC Board will begin planning during Summer 2013. The plan will be approved by ICC in early Fall and the implementation will begin as of September 2013, recess in October and November as to not conflict with the Thanksgiving Food Drive. The ICC Food Drive will reconvene February – early May 2014.
| FC Clubs/Organizations | ICC Board will coordinate the clubs and volunteers
Associated Students
| FC Faculty, Staff, Students | Student Affairs Classified Staff will inform the clubs & volunteers of details, and assist them as needed
Office of Special Programs
Volunteers
TECHNOLOGY & ENGINEERING
Action 1.1.48
The Administration of Justice Department will pilot a Law Enforcement hiring seminar to prepare recent graduates for the unique hiring process used to select law enforcement officers. | Classroom space, guest speakers, photocopied materials, and some classified staff support. | Department faculty - both full time and adjunct. | A two day function conducted during a weekend near the end of the spring term in synchronization with FCPA class completion. | A comparison will be made between hiring success rate for trial year as compared to prior years.
Action 1.1.49
The Administration of Justice Department will conduct a FCPA class family orientation to provide recruits and their families with insights into the rigors and demands of academy life and the expectations assumed in a law enforcement career. | Classroom space, guest speakers, photocopied materials, light refreshments, and some classified staff support. | Department faculty - both full time and adjunct. | A half day function conducted during a week prior to the beginning of the fall term in synchronization with the start of the FCPA. | A comparison will be made between retention rate for trial year as compared to prior years for academy exit other than for reasons of injury or academic dismissal. This will primarily track students leaving who indicate they were not well informed or lacked family support. This orientation does not replace the for credit class - AJ 094 Basic Police Academy Orientation.
Action 1.1.50
The Cosmetology Department will develop 2-3 new versions of short practice quizzes covering material from textbooks to reduce student fear of tests and improve understanding of the sciences used in Cosmetology. | Cosmetology full time staff using two major textbooks recommended by the California Board of Barbering and Cosmetology and Skill Center staff using special funding for this purpose. | Cosmetology full time staff and Skill Center staff. | Work begins during spring with results collected/ assessed during early fall 2013 The loop will close during the departments’ advisory committee meeting in October 2013 where recommendations for the next cycle will be recorded. | Students will be able to take the Cosmetology State examinations with increased confidence and knowledge leading to increased pass rates for State examinations. Pass rates are tracked and recorded by the department office.